|  | “APPROVED” Deputy Prime Minister – Minister of Culture and Information of the Republic of Kazakhstan _______________ A. G. Balaeva “____” ______________ 2025 |
| --- | --- |

National Action Plan of activities dedicated to the International Volunteer Year for Sustainable Development (hereinafter – the International Year)

| # | Activity | Timeline / Implementation period | Form of completion / Output | Responsible state body / agency |
| --- | --- | --- | --- | --- |

| 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- |
| Measures for institutional support of volunteering |  |  |  |  |
|  | Improvement of the operational infrastructure of Regional volunteer centers (front offices) | during the first quarter of 2026 | organization of the activities of front offices | Mayor’s offices of the cities of Astana, Almaty, Shymkent and the Regions |
|  | Development of new approaches and initiatives for the further advancement of the volunteer sector, including legislative amendments: - improvement of the status of volunteers; - introduction of a unified methodology for verifying the volunteer community; - introduction of an electronic volunteer document. | December 2026 | a package of approaches and initiatives | CGB, MCI, Mayor’s offices of the cities of Astana, Almaty, Shymkent and the Regions |
|  | Development of the National Volunteering Development Index and a methodology for measuring the volunteering sector. | December 2026 | Information | MCI, MTS, UNV (by mutual agreement) |
|  | Exploration of the introduction of digital systems and artificial intelligence in the volunteering sector. | December 2026 | Information | MCI, MAICD (by mutual agreement) |
|  | Organization of meetings of the National Organizing Committee for the observance of the International Year in coordination with the International Secretariat and partners. | quarterly, throughout 2026 | organization of meetings | MCI |
|  | Signing of an additional agreement between the Government of Kazakhstan and the United Nations Volunteers programme on the participation of Kazakhstani volunteers in UN international missions under the Full Funding Programme for 2027–2029. | December 2026 | signed agreement | MCI, MFA, MF |
|  | Exploration of improving the work of volunteer squads and groups based in educational institutions, including consideration of adopting a Model Regulation. | December 2026 | Information | MCI, MNHE, ME |
|  | Launch of a small grants competition to support volunteer initiatives on the occasion of the International Year. | January 2026 | small grants competition | MCI |
| International Events |  |  |  |  |
| As part of the implementation of the nationwide project “Taza Kazakhstan”: |  |  |  |  |
|  | Panel session “Volunteering and Environmental Action” as part of the Regional Environmental Summit | April 2026 | Panel session | MCI, MNER |
|  | Caspian Sea Action Week 2026 (ЦУР 14) — “Caspian Sea Action Week 2026” | August 2026 | Events | Mayor’s office of the Mangystau Region, MCI |
|  | Green Aral: Volunteers for Life – International Volunteer Week for the Restoration of the Aral Sea Region (SDG 15) | October 2026 | Events | Mayor’s office of the Kyzylorda Region, MCI |
|  | International Eco-Forum of Volunteers (SDG 13) | June 2026 | Furum | Mayor’s office of Karaganda Region, MCI |
|  | International Environmental Hackathon “Ecothon” (SDG 12) | September 2026 | environmental hackathon | Mayor’s office of Almaty, MCI |
| Promotions activities of the international volunteering |  |  |  |  |
|  | Holding the Forum of Volunteers of the Commonwealth of Independent States | August 2026 | Forum | MCI, MFA, Mayor’s office of Astana |
|  | International Conference “International Cooperation with UNV: Achievements, Challenges and New Horizons” | May 2026 | Conference | MCI, UNV |
|  | Healthy Future Forum (SDG 3) | May 2026 | Forum | Mayor’s office of Abai Region, MCI |
|  | EduBridge: Global Volunteer Forum for Inclusive Learning (SDG 4) | June 2026 | Forum | Mayor’s office of Pavlodar Region, MCI |
|  | Participation of volunteers in the organization of the International Multi-Sport Tournament “Games of the Future” | 2026 | provision of volunteers | MTS |
|  | Solemn presentation of the International “Volunteer of the Year” Award and the closing ceremony of the International Year | December 5, 2026 | Award ceremony | MCI |
| Country-Level Events |  |  |  |  |
|  | Organization of the National Launch of the International Year in the Republic of Kazakhstan | January 2026 | Event | MCI |
|  | Participation of the volunteer community in information and awareness-raising activities to promote the principle of “Law and Order” | Throughout the year | Information | MCI, Mayor’s offices of Astana, Almaty, Shymkent and the Regions |
|  | World Health Day: The contribution of volunteers to advancing the idea of “Health for All” and SDG 3 | April 2026 | Events | WHO, MH, and Mayor’s offices of the cities of Astana, Almaty, Shymkent, and the Regions |
|  | National Forum of Volunteers in Natural and Man-Made Emergency Response | September 2026 | Forum | MES |
|  | National Festival “VOLUNTEER FEST – 2026” | May 2026 | Festival | Mayor’ office of Zhambyl Region |
|  | National gathering of volunteers | August 2026 | Gathering | Mayor’s office of Kyzylorda Region |
|  | Interregional gathering of volunteers | September 2026 | Gathering | Mayor’s office of Kostanai Region |
|  | National campaign «16 days of activism against gender-based violence» | November 25 – December 10, 2026 | information campaign | MFA, UN Women |
|  | Organization of a national museum exhibition dedicated to the history and evolution of volunteering in Kazakhstan — from the traditions of Asar to modern volunteering | November-December 2026 | exhibition | MCI, National Museum (Upon agreement) |
| Regional Events |  |  |  |  |
|  | Organization of regional outreach meetings on the development of sectoral volunteering | first half of 2026 | organization of regional meetings and trainings | MCI, Mayor’s offices of Astana, Almaty, Shymkent and the Regions, НВС (по согласованию) |
|  | Organization of trainings and methodological activities to promote and advance volunteering | Throughout of 2026 | Events | MCI, Mayor’s offices of Astana, Almaty, Shymkent and the Regions |
|  | Organization of thematic museum exhibitions “From Asar to Modern Volunteering” | February-March 2026 | exhibitions | Mayor’s offices of Astana, Almaty, Shymkent and the Regions |
|  | Organization and holding of Health Days | March-April 2026 | events | Mayor’s offices of Astana, Almaty, Shymkent and the Regions |
|  | «Atyrau Volunteers Fest» Volunteer Festival | April 2026 | festival | Mayor’s office of Atyrau Region |
|  | Opening of the Volunteers’ Park | April-May 2026 | Park | Mayor’s office of Astana |
|  | «Birgemiz Fest» Volunteer Festival | July 2026 | festival | Mayor’s office of the North Kazakhstan Region |
|  | Volunteer regional gathering of the Zhetysu Region | July 2026 | gathering | Mayor’s office of the Zhetysu Region |
|  | Regional mini-grants competition | July-September 2026 | mini-grants competition | Mayor’s office of Kostanai Region |
|  | “Silver Volunteers of the Western Region” Gathering | September 2026 | gathering | Mayor’s office of Atyrau Region |
|  | Regional practice programme “Atyrau Youth Fellowship” | October 2026 | cases | Mayor’s office of Atyrau Region |
|  | Summit of Volunteers of the West Kazakhstan Region | November 2026 | summit | mayor’s office of the West Kazakhstan Region |
|  | Solemn awarding of citizens who have made a significant contribution to the development and support of volunteering | December 6, 2026 | Award Ceremony | CGB, Mayor’s offices of Astana, Almaty, Shymkent and the Regions |
| Information and awareness-raising activities |  |  |  |  |
|  | Preparation of the National Brand Book of the International Year for the implementation and support of the activities of the National Plan | December 31, 2025 | Brand book | MCI |
|  | Exploration of the development of a design layout for a postage stamp dedicated to the International Year of Volunteers for Sustainable Development | March 2026 | information | MCI, JSC “Kazpost” (by mutual agreement) |
|  | Creation of street murals on the theme of volunteering | May-September 2026 | murals | Mayor’s offices of Astana, Almaty, Shymkent and the Regions |
|  | Creation of a short film about volunteers and their contribution to sustainable development | December 2026 | Short film | MCI |
|  | Production and rotation of video messages from prominent public, cultural and government figures, including top officials, congratulating on the celebration of the International Year | Monthly, throughout 2026 | production of video clips and their rotation in the media | CGB, Mayor’s offices of Astana, Almaty, Shymkent and the Regions |
|  | Preparation and publication of a series of articles by representatives of the volunteer community dedicated to the celebration of the International Year | Monthly, throughout 2026 | publication on official online resources and legal information platforms | Mayor’s offices of Astana, Almaty, Shymkent and the Regions, MCI |
|  | Holding open lessons and lectures on the topic “Volunteering as a way of life” (with prior development and approval of a unified concept for this event and with the participation of representatives of the volunteer community) at schools, colleges and universities | February–May, September–December 2026 | holding of open lessons | Mayor’s offices of Astana, Almaty, Shymkent and the Regions, ME, MNHE, MCI |
|  | Series of articles and posts on the importance of the volunteering sector, and its promotion in the media and social networks (Instagram, TikTok, etc.) | Monthly, throughout 2026 | publication of materials in the media and social networks | Mayor’s offices of Astana, Almaty, Shymkent and the Regions, MCI |
|  | Organization of the national challenge “100 Volunteer Stories” | Monthly, throughout 2026 | publications on social media | MCI, NVS (upon agreement) |
|  | Organization of a podcast on the YouTube channel “People Who Make Changes” | Monthly, throughout 2026 | publications on social media | MCI, NVS (upon agreement) |
|  | Broadcast of thematic radio programmes on volunteering | Monthly, throughout 2026 | release of podcasts, live broadcasts, and interviews | Mayor’s offices of Astana, Almaty, Shymkent and the Regions |

Note: explanation of abbreviations:
1. JSC – Joint Stock Company;
2. Mass Media – Mass Media;
3. UNV – United Nations Volunteers programme;
4. MNHE – Ministry of Science and Higher Education of the Republic of Kazakhstan;
5. WHO – World Health Organization;
6. MH – Ministry of Health of the Republic of Kazakhstan;
7. MAICD – Ministry of Artificial Intelligence and Digital Development of the Republic of Kazakhstan;
8. MIA – Ministry of Internal Affairs of the Republic of Kazakhstan;
9. MF – Ministry of Finance of the Republic of Kazakhstan;
10. MCI – Ministry of Culture and Information of the Republic of Kazakhstan;
11. MTS – Ministry of Tourism and Sports of the Republic of Kazakhstan;
12. ME – Ministry of Education of the Republic of Kazakhstan;
13. CGB – Central government bodies;
14. MFA – Ministry of Foreign Affairs of the Republic of Kazakhstan;
15. SDGs – Sustainable Development Goals;
16. MES – Ministry of Emergency Situations of the Republic of Kazakhstan;
17. NVS – National Volunteer Network;
18 NOC – National Organizing Committee;
19. BNS – Bureau of National Statistics;
20. MNER – Ministry of Ecology and Natural Resources of the Republic of Kazakhstan.